|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Task | Start time | Finish time | Implemented by | Evaluation(%) |
| Feasibility study phase |  |  |  |  |
| Evaluate and analyze idea | 16/10/2020 | 20/10/2020 | VU TRAN QUANG | 30 |
| Provide opinions and idea | 16/10/2019 | 20/10/2020 | KHOI NGUYEN DAM | 25 |
| Provide opinions and idea | 16/10/2019 | 20/10/2020 | LONG NGUYEN THE | 25 |
| Approve and finalize idea | 20/10/2020 | 23/10/2020 | VU TRAN QUANG | 20 |
| Requirement Analysis phase |  |  |  |  |
| Propose system | 23/10/2020 | 25/10/2020 | KHOI NGUYEN DAM | 50 |
| Analyze and approve final system | 25/10/2020 | 27/10/2020 | VU TRAN QUANG | 50 |
| Design phase |  |  |  |  |
| Design Database | 28/10/2020 | 3/11/2020 | VU TRAN QUANG | 50 |
| Design basic static client and admin | 28/10/2020 | 3/11/2020 | LONG NGUYEN THE | 50 |
| Development phase |  |  |  |  |
| Client site – Home Page | 3/11/2020 | 10/11/2020 | VU TRAN QUANG | 20 |
| Client site – Search, Order detail | 3/11/2020 | 11/11/2020 | LONG NGUYEN THE | 10 |
| Client site – Check out and payment | 11/11/2020 | 20/11/2020 | VU TRAN QUANG | 10 |
| Client site – Cancel and Reschedule | 3/11/2020 | 11/11/2020 | KHOI NGUYEN DAM | 10 |
| Admin site – Manage country, airline, aircraft, flight distance | 11/11/2020 | 22/11/2020 | KHOI NGUYEN DAM | 10 |
| Admin site – Manage route | 20/11/2020 | 28/11/2020 | VU TRAN QUANG | 20 |
| Admin site – – Manage flight, customer | 11/11/2020 | 22/11/2020 | LONG NGUYEN THE | 10 |
| Admin site – Manage employee | 22/11/2020 | 30/11/2020 | KHOI NGUYEN DAM | 10 |
| Testing phase – Delete page |  |  |  |  |
| Testing client site | 30/11/2020 | 02/12/2020 | KHOI NGUYEN DAM | 30 |
| Testing admin site | 30/11/2020 | 03/12/2020 | LONG NGUYEN THE | 30 |
| Final testing, fixing bugs | 30/11/2020 | 03/12/2020 | VU TRAN QUANG | 40 |
| Deployment phase |  |  |  |  |
| Analyze and approve final product | 03/12/2020 | 05/12/2020 | LONG NGUYEN THE | 50 |
| Write product report | 03/12/2020 | 05/12/2020 | VU TRAN QUANG | 50 |